## Project Tracker
MassageNearMe - Project Tracker
Development: 29/29 Complete ¦ Deployment: 0/14 ¦ Config: 0/6
# | Task | Status | Notes
📁 DEVELOPMENT - CODE FILES
1 | Backend API (server.js) | ✅ Done | Node.js + Express server
2 | Database Schema (schema.sql) | ✅ Done | PostgreSQL with geo queries
3 | Auth Routes (auth.js) | ✅ Done | Login, Register, JWT
4 | Search Routes (search.js) | ✅ Done | Zip code radius search
5 | Therapist Routes (therapists.js) | ✅ Done | Profile CRUD, dashboard
6 | Booking Routes (bookings.js) | ✅ Done | Appointments management
7 | Payment Routes (payments.js) | ✅ Done | Stripe subscriptions
8 | Service Routes (services.js) | ✅ Done | Massage types
9 | Auth Middleware | ✅ Done | JWT verification
10 | Frontend - index.html | ✅ Done | Landing page with search
11 | Frontend - search.html | ✅ Done | Search results page
12 | Frontend - therapist.html | ✅ Done | Profile page
13 | Frontend - login.html | ✅ Done | Auth page
14 | Frontend - dashboard.html | ✅ Done | Therapist dashboard
15 | CSS - All stylesheets | ✅ Done | styles, search, auth, dashboard, therapist
16 | JS - config.js | ✅ Done | API config with auto-detect URL
17 | JS - app.js | ✅ Done | Common functions, SW registration
18 | JS - home.js | ✅ Done | Homepage logic
19 | JS - search.js | ✅ Done | Search functionality
20 | JS - therapist.js | ✅ Done | Profile page logic
21 | JS - auth.js | ✅ Done | Login/register logic
22 | JS - dashboard.js | ✅ Done | Dashboard functionality
23 | PWA - manifest.json | ✅ Done | App manifest
24 | PWA - sw.js | ✅ Done | Service worker with caching
25 | PWA - Icons (all sizes) | ✅ Done | 72-512px PNG icons
26 | Railway - api/railway.json | ✅ Done | API deployment config
27 | Railway - frontend/static.json | ✅ Done | Static site config
28 | DB - import-zipcodes.js | ✅ Done | US zip code importer
29 | README.md | ✅ Done | Full deployment guide
🚀 DEPLOYMENT STEPS
1 | Create GitHub repository | ⏳ Pending | github.com/new → name: massage
2 | Push code to GitHub | ⏳ Pending | git push -u origin main
3 | Create Railway project | ⏳ Pending | railway.app → New Project
4 | Add PostgreSQL database | ⏳ Pending | New → Database → PostgreSQL
5 | Add API service | ⏳ Pending | New → GitHub Repo → Root: api
6 | Add Frontend service | ⏳ Pending | New → GitHub Repo → Root: frontend
7 | Set API environment variables | ⏳ Pending | See Configuration section
8 | Link PostgreSQL to API | ⏳ Pending | Variables → DATABASE_URL
9 | Generate API domain | ⏳ Pending | Settings → Networking
10 | Generate Frontend domain | ⏳ Pending | Settings → Networking
11 | Run database schema | ⏳ Pending | psql $DATABASE_URL < db/schema.sql
12 | Import zip codes | ⏳ Pending | npm run db:import-zips
13 | Test API health endpoint | ⏳ Pending | curl https://api-url/health
14 | Test frontend loads | ⏳ Pending | Open frontend URL in browser
⚙️ CONFIGURATION - ENVIRONMENT VARIABLES
1 | NODE_ENV | ⏳ Pending | Set to: production
2 | JWT_SECRET | ⏳ Pending | Generate 64-char random string
3 | FRONTEND_URL | ⏳ Pending | https://massage.aiappspro.com
4 | DATABASE_URL | ⏳ Pending | Auto-set by Railway PostgreSQL link
5 | STRIPE_SECRET_KEY | ⏳ Pending | From Stripe Dashboard (sk_live_xxx)
6 | STRIPE_WEBHOOK_SECRET | ⏳ Pending | After creating webhook (whsec_xxx)
💳 STRIPE SETUP
1 | Create Stripe account | ⏳ Pending | stripe.com
2 | Create Pro product ($49/mo) | ⏳ Pending | Products → Add Product
3 | Create Premium product ($99/mo) | ⏳ Pending | Products → Add Product
4 | Create webhook endpoint | ⏳ Pending | Developers → Webhooks
5 | Update subscription_plans table | ⏳ Pending | Add stripe_price_id values
🌐 CUSTOM DOMAIN (OPTIONAL)
1 | Add CNAME: massage → railway-frontend | ⏳ Pending | DNS registrar
2 | Add CNAME: api-massage → railway-api | ⏳ Pending | DNS registrar
3 | Configure Railway custom domains | ⏳ Pending | Settings → Networking → Custom Domain
4 | Update FRONTEND_URL env var | ⏳ Pending | To match custom domain
🔮 FUTURE ENHANCEMENTS (OPTIONAL)
1 | Pricing page (pricing.html) | ⏳ Future | For therapist signup funnel
2 | Image upload (S3/Cloudinary) | ⏳ Future | Profile & gallery images
3 | Email notifications (SendGrid) | ⏳ Future | Booking confirmations
4 | SMS reminders (Twilio) | ⏳ Future | Appointment reminders
5 | Admin dashboard | ⏳ Future | Manage users, view stats
6 | Analytics integration | ⏳ Future | Google Analytics, Mixpanel
7 | SEO optimization | ⏳ Future | Meta tags, sitemap, structured data